## C01_FA
Financial Analysis for WasteGone
Created by: Daniele Fabiano, Francesco Paolo D'Antuono
Discount rate | 8%
Assume the project is completed in Year 0 |  |  | Year
| 0 | 1 | 2 | 3 | Total
Costs | 133300 | 30500 | 30500 | 30500
Discount factor | 1 | 0.93 | 0.86 | 0.79
Discounted costs | 133300 | 28365 | 26230 | 24095 | 211990
Benefits | 0 | 85500 | 85500 | 85500
Discount factor | 1 | 0.93 | 0.86 | 0.79
Discounted benefits | 0 | 79515 | 73530 | 67545 | 220590
Discounted benefits - costs | -133300 | 51150 | 47300 | 43450 | 8600 | NPV
Cumulative benefits - costs | -133300 | -82150 | -34850 | 8600
ROI | 4.057%
Payback in Year 3
Assumptions
Costs | N. Resources | Cost/Hour | Hour |  | Total cost
Project Manager | 2 | 40 | 768 |  | 30720
Team Leader | 1 | 35 | 384 |  | 13440
Sviluppatore | 6 | 30 | 2304 |  | 69120
Server e hosting cloud |  |  |  |  | 5980
Software e licenze |  |  |  |  | 4040
Dispositivi per la digitalizzazione dei rifiuti |  |  |  |  | 10000
Total Project Costs (applied in year 0) |  |  |  |  | 133300 | €
Project Costs (applied in year 1/2/3)
Costs |  |  |  |  | Total cost
Manutenzione tecnica |  |  |  |  | 10000
Server e hosting cloud |  |  |  |  | 4000
Supporto utenti |  |  |  |  | 4000
Campagne di marketing |  |  |  |  | 9000
Eventi di sensibilizzazione |  |  |  |  | 3500
Total Project Costs (applied in year 1/2/3) |  |  |  |  | 30500 | €
Benefits
Risparmio di carta |  |  |  |  | 23000
Riduzione costi gestione rifiuti |  |  |  |  | 19000
Riduzione impatto ambientale |  |  |  |  | 11000
Pubblicizzazione eventi di terzi |  |  |  |  | 12500
Sponsorship con aziende green |  |  |  |  | 20000
Total Project Benefits |  |  |  |  | 85500 | €

## C01_CB
COSTI | TEMPO
39086 | OTTOBRE
53344 | NOVEMBRE
65931 | DICEMBRE
90711 | GENNAIO
115491 | FEBBRAIO
142631 | MARZO

## C01_FE
COSTI | TEMPO |  | 2024 |  |  | 2025
39086 | OTTOBRE | MESE | OTTOBRE | NOVEMBRE | DICEMBRE | GENNAIO | FEBBRAIO | MARZO
53344 | NOVEMBRE | COSTI | 39086 | 14258 | 12587 | 24780 | 24780 | 27140
65931 | DICEMBRE | TOTALE SPESO | 39086 | 53344 | 65931 | 90711 | 115491 | 142631
90711 | GENNAIO | TRASFERIMENTI | 45000 | 30000 | - | 45000 | - | 30000
115491 | FEBBRAIO | FONDI TOTALI | 45000 | 75000 | 75000 | 120000 | 120000 | 150000
142631 | MARZO | DENARO SUL CONTO | 5914 | 21656 | 9069 | 29289 | 4509 | 7369
45000
75000
75000
120000
120000
150000